## Sheet1
Project 1 - __________________ Data Analysis
Preparation Phase
Task | Start Date | End Date | Responsibility | Status | Comments
Gather information on topic | 2019-02-16 | 2019-02-19 | Team | In Progress | Each team member work on a topic before start of 2/19/2019 class for class discussion
Discuss topic in class | 2019-02-19 | 2019-02-19 | Team | To do | Make decision in class
Figure out work assignments | 2019-02-19 |  | Team | To do | each teammate work on specific data set/plotting and then merge scripts together???
Execution Phase
Begin coding for assigned work | 2019-02-21 |  | Team | To do
Progress checkpoint 1 | 2019-02-21 | 2019-02-21 | Team | To do | Check in with progress, help if needed
Progress checkpoint 2 | 2019-02-23 |  | Team | To do | Check in with progress, help if needed
QA Phase
QA Script, check for errors | 2019-02-26 | 2019-02-26 | Team | To do | In class, go over script, look for logic/syntax errors
Add summary comments to Jupyter Notebook | 2019-02-26 |  | Team | To do
Completion Phase
Work on summary document | TBD |  | Team | To do
Practice speech | TBD |  | Team | To do
Class Presentation | TBD |  | Team | To do